## Introduction
Scrum Master Rajesh Thapa
Developer Biraj Sharma
Developer Anish Gautam
Developer Samjhana Dahal
Developer Sulav Karki
Konnekt
(Social Media)

## User Story Without Priority
LIST OF USER STORIES
S.N. | User Story | Acceptance Criteria
1 | As a user, I want to send and receive messages instantly so that I can communicate in real time. | • Messages appear instantly. • Recipient receives without refresh
2 | As a user, I want to see when someone is typing or online so I know their activity. | • Shows "typing…" indicator. • Online/offline status updates in real-time.
3 | As a user, I want to see if my message is read so I understand communication status. | • Shows delivered/read status. • Ticks or indicator updates instantly.
4 | As a user, I want to make audio calls for smooth communication. | • Start/end audio call. • Low latency. • Incoming call alert
5 | As a user, I want to make video calls to see the person I’m talking to. | • High-quality stream. • Mute/unmute, switch camera.
6 | As a user, I want to create posts with text/media so I can share updates. | • Uploads text/images/videos. • Appears instantly
7 | As a user, I want to react to posts to engage with others. | • Like/unlike. • Comment instantly. • Share posts.
8 | As a user, I want a personalized news feed so I see relevant content. | • Shows followed users’ posts. • Sorted by recency
9 | As a user, I want to register and log in using a secure authentication system. | • Shows DP, bio, posts. • Applies privacy settings
10 | As a user, I want to create my profile with a display picture and bio. | • Upload profile picture. • Edit bio. • Changes save instantly
11 | As a user, I want to view other people’s profiles and posts. | • Shows DP, bio, posts. • Applies privacy settings
12 | As a user, I want notifications for likes, comments, and messages. | • Instant notifications. • Shows sender + action. • Can mark as read.
13 | As a user, I want push notifications even when offline. | • Works when the app is closed. • Open the correct screen on tap.
14 | As a user, I want to search users, posts, and groups. | • Live search results. • Trending suggestions appear.
15 | As a user, I want harmful content to be filtered automatically | • Java AI/NLP toxicity model flags/blocks abusive words.
16 | As a user, I want to write posts offline and auto-upload when online. | • Instant uploads when back online.

## Agile User Story
AGILE USER STORY
Feature ID | Feature Name | User Story ID | Priority | As a <Type of user> | I need to <perform some task> | So that I can <achieve something> | Acceptance Criteria
F1 | Real-Time Messaging | 1.1 | High | User | send and receive messages instantly | communicate in real time | Messages are delivered instantly without refresh; receiver receives messages immediately.
F2 | Typing & Online Status | 1.2 | Low | User | see typing and online status | know other user activity | Typing indicator is shown; online/offline status updates in real time.
F3 | Message Read Receipts | 1.3 | Low | User | view message read status | track communication status | Delivered and read indicators are displayed instantly.
F4 | Audio Calls | 1.4 | High | User | make audio calls | communicate smoothly | User can start and end calls; incoming call alert shown; low latency audio.
F5 | Video Calls | 1.5 | High | User | make video calls | see the other user | High-quality video; mute/unmute supported; camera switch available.
F6 | Real-Time Notifications | 1.6 | Low | User | receive notifications | / | Notifications appear instantly; sender and action displayed; can mark as read.
F7 | Social Posting | 2.1 | Medium | User | create posts with text or media | share updates | Upload text/images/videos; post appears instantly in feed.
F8 | Likes, Comments & Shares | 2.2 | Low | User | like, comment, and share posts | interact with others | Like/unlike works; comments appear instantly; posts can be shared.
F9 | Personalized Feed | 2.3 | Medium | User | view other user profiles | see relevant content | Shows followed users’ posts; sorted by recency.
F10 | User Profile Setup | 2.4 | Medium | User | register and login securely | protect my account | Spring Security login; password hashing; JWT/session supported.
F11 | View Other Profiles | 2.5 | Medim | User | create and update profile | present my information | Upload profile picture; edit bio; changes saved instantly.
F12 | Real-Time Notifications | 2.6 | Low | User | view other user profiles | see their details and posts | Shows profile picture and bio; privacy settings applied.
F13 | Push Notifications | 3.1 | Low | User | receive notifications when offline | not miss updates | Notifications work when app is closed; correct screen opens on tap.
F14 | Search & Discovery | 3.2 | Medium | User | search users and posts | discover content | Live search results displayed; trending suggestions shown.
F15 | Toxicity Filter | 3.3 | Medium | User | filter harmful content | keep platform safe | Toxic words detected using AI/NLP; abusive content blocked.
F16 | Offline Draft Posts | 3.4 | Low | User | write posts offline | upload later | Posts saved offline; auto-upload when internet is restored.
|  | 3.6 | Low | User | see read time | track response delay | • Access and go through the book available in the system either by exploring the list or by searching it directly. • Display a 'Share' button next to the 'Add to Favourites' button. • Click the button to access the modal with hyperlink of the book. • Copy the hyperlink and share it in other social medias.

## User Story Priority Hierarchy
AGILE USER STORY - HIERARCHY
Feature ID | User Story Id | Priority | As a <Type of user> | I need to <perform some task> | So that I can <achieve something> | Acceptance Criteria
F1 | 1.1 | High | User | send and receive messages instantly | communicate in real time | • Messages appear instantly • Recipient receives without refresh
F1 | 1.2 | High | User | make audio calls | communicate smoothly through voice | • Audio call can start/end • Low latency • Incoming call alert
F1 | 1.3 | High | User | make video calls | see the person I am talking to | • High-quality video stream • Mute/unmute available • Camera switch supported
F1 | 1.5 | High | User | create posts with text or media | share updates | • Upload text/images/videos • Appears instantly
F2 | 2.3 | High | User | register and log in securely | access the system safely | • Spring Security authentication • Password hashed • Session/JWT supported
F2 | 2.4 | High | User | receive notifications | not miss likes, comments, or messages | • Instant notifications • Shows sender and action
F2 | 2.5 | High | User | have harmful content filtered | use a safe platform | • Java AI/NLP detects toxic words • Abusive content blocked
F3 | 3.1 | High | User | write posts offline | not lose content | • Draft saved offline • Auto-upload when online
F1 | 1.6 | Medium | User | see typing and online status | know other users’ activity | • Typing indicator shown • Online/offline updates in real time
F2 | 2.1 | Medium | User | see message read receipts | understand communication status | • Delivered/read indicators update instantly
F3 | 3.5 | Medium | User | like, comment, and share posts | engage with others | • Like/unlike supported • Comments appear instantly • Posts can be shared
F4 | 4.1 | Medium | User | view a personalized feed | see relevant content | • Shows followed users’ posts • Sorted by recency
F4 | 4.1 | Medium | User | set up my profile with photo and bio | personalize my profile | • Upload profile picture • Edit bio • Changes saved instantly
F4 | 4.1 | Medium | User | view other users’ profiles | see their information and posts | • Displays profile picture, bio, posts • Privacy applied
F4 | 4.1 | Medium | User | search users, posts, and groups | find content easily | • Live search results • Trending suggestions
F1 | 1.4 | Low | User | receive push notifications when offline | stay informed outside the app | • Works when app is closed • Opens correct screen

## User Story Map Board
Legend : US - User Story
The Backbone | Epic 1 | Epic 2 | Epic 3 | Epic 4
Flesh on the backbone | User Account & Profile | Communication | Social Interaction | System & Administration
Sprint / Iteration 1 (07/12/2025 – 13/12/2025) | US 10- User profile and setup
SEQUENCE | US 8 - Personalized Feed
Version 1.0 | US 7 - Like / Comment / Share
US 11 - Profile Viewing
Sprint / Iteration 2 (14/12/2025 – 20/12/2025) |  | US 1 – Real-time Messaging
Version 2.0 |  |  | US 9 - Video and Audio call
US 15 - Followers&Social Posting
US 2,3- Inbox online status and receipts
Sprint / Iteration 3 (21/12/2025 – 27/12/2025) |  |  |  | US 12 – Settings & Push Notifications
US 13 – Real-Time Notifications
US 9 – Password & Authentication
Sprint / Iteration 4 (28/12/2025 – 03/01/2026) |  | US 15 – Admin Panel
Version 4.0 |  | US 14 – Search & Discovery
US 16 – Membership Handling
RELEASE THEME: Konnekt – Social Media Application

## Agile Release Plan
AGILE RELEASE PLAN
AT RISK | SPRINT | USER STORY NAME | FEATURE TYPE | START | FINISH | DURATION (In Hours) | STORY POINTS | STATUS | RELEASE DATE
| 1 | User Story 10 – User Profile setup | Functionality | 2025-07-12 | 2025-09-12 | 9 | 2 | Planned
| 1 | User Story 8 – Personalized Feed | Functionality | 2025-07-12 | 2025-10-12 | 9 | 2 | Planned
| 1 | User Story 7 – Like / Comment / Share | Functionality | 2025-08-12 | 2025-11-12 | 12 | 3 | Planned
| 1 | User Story 11 – Profile Viewing | Functionality | 2025-09-12 | 2025-09-12 | 6 | 1 | Planned | 13/12/2025
| 2 | User Story 1 – Real-time Messaging | Functionality | 14/12/2025 | 14/12/2025 | 9 | 2 | Planned
| 2 | User Story 4 & 5 – Video / Audio Call | Functionality | 15/12/2025 | 15/12/2025 | 9 | 2 | Planned
| 2 | User Story 6 – Followers & Social Posting | Functionality | 16/12/2025 | 16/12/2025 | 6 | 1 | Planned
| 2 | User Story 2 & 3 – Inbox (Online Status & Read Receipts | Functionality | 17/12/2025 | 17/12/2025 | 9 | 2 | Planned | 20/12/2025
| 3 | User Story 12-Settings & Push Notification | Functionality | 21/12/2025 | 22/12/2025 | 12 | 3 | Planned
| 3 | User Story 9-Password & Authentication | Functionality | 23/12/2025 | 24/12/2025 | 12 | 3 | Planned
| 3 | User Story 13-Real-Time Notifications | Functionality | 25/12/2025 | 25/12/2025 | 9 | 2 | Planned | 27/12/2025
| 4 | User Story 15-Admin Panel | Functionality | 28/12/2025 | 28/12/2025 | 9 | 2 | Planned
| 4 | User Story 14-Search & Discovery | Functionality | 29/12/2025 | 29/12/2025 | 6 | 1 | Planned
| 4 | User Story 13-Membership Handling | Functionality | 30/12/2025 | 30/12/2025 | 6 | 1 | Planned | 2026-03-01

## Agile Sprint 1 Backlog
AGILE SPRINT 1 BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #10 : User Profile Setup | 1.5 |  |  | 9
Frontend |  | Biraj Sharma | Done | 1.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 1.5
Backend |  | Biraj Sharma | Done | 3 | 0 | 0.5 | 1 | 1 | 0 | 2.5
Database |  | Biraj Sharma | Done | 2 | 0 | 0 | 1 | 0.5 | 1 | 2.5
Testing |  | Biraj Sharma & Team | Done | 1 | 0 | 0 | 0 | 1 | 0.5 | 1.5
Validation |  | Biraj Sharma & Team | Done | 1.5 | 0 | 0 | 0 | 0.5 | 0.5 | 1
User Story #8 : Personalized Feed | 1.5 |  |  | 9
Frontend |  | Samjhana Dahal | Done | 2.5 | 1 | 1.5 | 0 | 0 | 0 | 2.5
Backend |  | Samjhana Dahal | Done | 2 | 0 | 1 | 1 | 0 | 0 | 2
Database |  | Samjhana Dahal | Done | 2 | 0 | 1 | 1 | 0.5 | 0 | 2.5
Testing |  | Samjhana Dahal & Team | Done | 1.5 | 0 | 0 | 0 | 1 | 0 | 1
Validation |  | Samjhana Dahal & Team | Done | 0.5 | 0 | 0 | 0 | 0 | 1 | 1
User Story #7 : Like/Comment/Share | 2 |  |  | 12
Frontend |  | Rajesh Thapa | Done | 1 | 1 | 0.5 | 0 | 0 | 0 | 1.5
Backend |  | Rajesh Thapa | Done | 4 | 2 | 1 | 1 | 0 | 0 | 4
Database |  | Rajesh Thapa | Done | 3 | 0 | 0 | 0.5 | 1 | 1 | 2.5
Testing |  | Rajesh Thapa & Team | Done | 2 | 0 |  | 1 | 1 | 1 | 3
Validation |  | Rajesh Thapa & Team | Done | 2 | 0 |  | 0 | 1 | 1 | 1
User Story #11 : Profile Viewing | 1 |  |  | 6
Frontend |  | Anish Gautam | Done | 1 | 1 | 0 | 0 | 0 | 0 | 1
Backend |  | Anish Gautam | Done | 2 | 0 | 0.5 | 1 | 0.5 | 0 | 2
Database |  | Anish Gautam | Done | 1 | 0 | 1 | 0.5 | 0 | 0 | 1.5
Testing |  | Anish Gautam & Team | Done | 1 | 0 | 0 | 0 | 0.5 | 0 | 0.5
Validation |  | Anish Gautam & Team | Done | 1 | 0 | 0 | 0 | 0.5 | 0 | 0.5
TOTAL |  |  |  | 36 | 5.5 | 6 | 8.5 | 9 | 6 | 36.5
IDEAL |  |  |  | 36 | -1.7 | -1.2 | 1.3 | 1.8 | -1.2 | 36

## Agile Sprint 2 Backlog
AGILE SPRINT 2 BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1 : Real-time Messaging | 1.5 |  |  | 9
Frontend |  | Samjhana Dahal | Done | 1.5 |  | 0.5 | 1 | 0 | 0 | 2
Backend |  | Samjhana Dahal | Done | 2.5 | 0 | 1 | 1 | 0 | 0 | 2
Database |  | Samjhana Dahal | Done | 1.5 | 0 | 0 | 1 | 1 | 0.5 | 2.5
Testing |  | Samjhana Dahal & Team | Done | 1.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
Validation |  | Samjhana Dahal & Team | Done | 2 | 0 | 0 | 0 | 1 | 0.5 | 1.5
User Story #4&5 : Video/Audio call | 1.5 |  |  | 9
Frontend |  | Rajesh Thapa | Done | 1 | 1 | 0 | 0 | 0 | 0 | 1
Backend |  | Rajesh Thapa | Done | 3 | 1 | 1 | 1 | 1 | 0 | 4
Database |  | Rajesh Thapa | Done | 2 | 0 | 0.5 | 1 | 0.5 | 0.5 | 2.5
Testing |  | Rajesh Thapa & Team | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Validation |  | Rajesh Thapa & Team | Done | 1 | 0 | 0 | 0 | 0 | 1 | 1
User Story #6 : Followers & Social Posting | 1 |  |  | 6
Frontend |  | Anish Gautam | Done | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 1
Backend |  | Anish Gautam | Done | 2 | 0 | 0.5 | 0.5 | 1 | 0 | 2
Database |  | Anish Gautam | Done | 2 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Testing |  | Anish Gautam & Team | Done | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0.5
Validation |  | Anish Gautam & Team | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #2 &3 : Inbox( Online Status & Read Receipts) | 1.5 |  | Planned | 9
Frontend |  | Biraj Sharma | Done | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 1
Backend |  | Biraj Sharma | Done | 4 | 1.5 | 1 | 2 | 0 | 0 | 4.5
Database |  | Biraj Sharma | Done | 2 | 0 | 0 | 1 | 1 | 0 | 2
Testing |  | Biraj Sharma | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Validation |  | Biraj Sharma & Team | Done | 1 | 0 | 0 | 0 | 0 | 0.5 | 1
TOTAL |  |  |  | 33 | 5 | 5.5 | 8.5 | 7.5 | 5.5 | 32.5
IDEAL |  |  |  |  | -1.6 | -1.1 | 1.9 | 0.9 | -1.1

## Agile Sprint 3 Backlog
AGILE SPRINT 3 BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #13 : Settings & Push notification | 2 |  |  | 12
Frontend |  | Anish Gautam | Done | 1 | 1 | 1 | 1 | 0 | 0 | 3
Backend |  | Samjhana Dahal | Done | 4 | 1 | 1 | 1 | 1 | 0 | 4
Database |  | Anish Gautam | Done | 4 | 0 | 0 | 1 | 1 | 2 | 4
Testing |  | Samjhana Dahal | Done | 1.5 | 0 | 0 | 0.5 | 0 | 1 | 1.5
Validation |  | Anish Gautam & Samjhana Dahal | Done | 1 | 0 | 0 | 0 | 0 | 1 | 1
User Story #9: Password and Password Authentication | 2 |  |  | 12
Frontend |  | Sulav Karki | Done | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 1
Backend |  | Biraj Sharma | Done | 5 | 1 | 2 | 2 | 0 | 0 | 5
Database |  | Biraj Sharma | Done | 4 | 0 | 1 | 1 | 2 | 0 | 4
Testing |  | Biraj Sharma | Done | 1 | 0 | 0 | 0.5 | 0 | 0.5 | 1
Validation |  | Biraj Sharma & Team | Done | 1 | 0 | 0 | 0 | 0 | 1 | 1
User Story #12 : Real-Time Notifications | 1.5 |  |  | 9
Frontend |  | Rajesh Thapa | Done | 1 | 1 | 0 | 0 | 0 | 0 | 1
Backend |  | Rajesh Thapa | Done | 3 | 1 | 2 | 0 | 0 | 0 | 3
Database |  | Rajesh Thapa | Done | 3 | 0 | 1 | 1 | 1 | 0 | 3
Testing |  | Rajesh Thapa | Done | 1 | 0 | 0 | 0 | 0.5 | 0.5 | 1
Validation |  | Rajesh Thapa | Done | 1 | 0 | 0 | 0 | 0 | 1 | 1
TOTAL |  |  |  | 33 | 5.5 | 8.5 | 8 | 5.5 | 5.5 | 34.5
IDEAL |  |  |  |  | -1.1 | 1.9 | 1.4 | -1.1 | -1.1

## Agile Sprint 4 Backlog
AGILE SPRINT 4 BACKLOG
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE (In Hours) | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #15 : Admin Panel | 1.5 |  |  | 9
Frontend |  | Samjhana dahal | Done | 2 | 2 | 0 | 0 | 0 | 0 | 2
Backend |  | Rajesh Thapa | Done | 3 | 1 | 1 | 1 | 0 | 0 | 3
Database |  | Rajesh Thapa | Done | 2.5 | 0 | 1 | 0 | 1 | 1 | 3
Testing |  | Samjhana dahal | Done | 1 | 0 | 0 | 0 | 1 | 0 | 1
Validation |  | Rajesh Thapa | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #14 : Search & Discovery | 1 |  |  | 6
Frontend |  | Anish Gautam | Done | 1 | 1 | 0 | 0 | 0 | 0 | 1
Backend |  | Biraj Sharma | Done | 2 | 0 | 1 | 1 | 0 | 0 | 2
Database |  | Biraj Sharma | Done | 2 | 0 | 1 | 1 | 0.5 | 0 | 2.5
Testing |  | Anish Gautam | Done | 0.5 | 0 | 0 | 0 | 0 | 1 | 1
Validation |  | Anish Gautam | Done | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5
User Story #Membership Handeling | 2 |  |  | 12
Frontend |  | Biraj Sharma | Done | 3 | 2 | 1 | 0 | 0 | 0 | 3
Backend |  | Rajesh Thapa | Done | 4 | 0 | 1 | 3 | 0 | 0 | 4
Database |  | Rajesh Thapa | Done | 2 | 0 | 1 | 1 | 0 | 0.5 | 2.5
Testing |  | Anish Gautam | Done | 2 | 0 | 0 | 0 | 2 | 0 | 2
Validation |  | Samjhana Dahal | Done | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.5
TOTAL |  |  |  | 27 | 6 | 7 | 7 | 4.5 | 4 | 28.5
IDEAL |  |  |  |  | 0.6 | 1.6 | 1.6 | -0.9 | -1.4